## Estimating template guidelines
Delete this sheet before submitting estimate
Start with "the Costs number" provided in the Business Case during Phase 0 …
Project Costs as defined in the Business Case template instructions are:
…. any costs related to completing this project including: development costs,
software costs, hardware costs, etc. as well as ongoing support costs.
As a starting point, apportion the cost dollars across the Phases of the project. (Tops Down estimate)
Further breakdown the phases of the project into a task/activity list for each phase.
Estimate the effort & costs for the project against the task/activity list (see the "effort" tab)
(Consider the following areas in estimating your software development (or upgrade) project :)
Development Effort - (time*rate) by resource type, by project phase, by task/activity
Hardware Costs
Software Costs
Networks
On-going support Costs
Admin costs (above typical overhead)
For increased accuracy, re-estimate the project using a bottoms up approach and reconcile the major differences
between the Top down and the Bottoms up estimates.(Whenever possible seek an independent validation of the
estimate before providing it to your Client.)
Document the risks assessed and assumptions made that support the estimate.
The various tabs in this workbook are intended as aids in estimating I.S. projects.
Please note … the various sample tables, and estimating checklists, used throughout the workbook are intended as
guidelines or examples for potential tables to be used for individual projects. In many cases, experienced
Project Managers will have far more sophisticated tables that will better serve the project. These should
definitely be substituted for the table in the workbook. Where the Project Manager does not have such an instrument,
the workbook tables might serve as a base for what is needed for the project being estimated.
The colors and markings in this workbook have the following meanings.
Green Cells = Calculated Numbers
Gray Cells = numbers or fields to be supplied by template user.
Project: Encompassing the totality of the undertaking. | Other colors/patterns have no meaning other than formatting
See the estimating Workbook presentation for information on how to use the estimating tabs.