## S_Curve_Progress
PROJECT PROGRESS TRACKER - S-CURVE
Time Period | Planned Progress (Cumulative) | Actual Progress (Cumulative) | Variance (Actual - Planned)
Week 1 | 2% | 2% | 0%
Week 2 | 8% | 6% | -2%
Week 3 | 18% | 14% | -4%
Week 4 | 35% | 28% | -7%
Week 5 | 55% | 45% | -10%
Week 6 | 75% | 60% | -15%
Week 7 | 88% | 72% | -16%
Week 8 | 95%
Week 9 | 99%
Week 10 | 100%