## Welding_Inspection_Log
WELDING INSPECTION LOG (QA/QC)
Project Name: | Pipeline Expansion Phase 2 |  | Report No: | WIL-2026-04
Contractor: | Apex Welding Services |  | Date: | 2026-03-06
Lead Inspector: | John Smith (CSWIP 3.1) |  | Applicable Code: | ASME B31.3
Date Inspected | Joint / Weld No. | Line / Iso Ref. | Welder ID | WPS No. | Mat. & Thk (mm) | NDT Method | Result | Defect Code (If Any) | Repair Ref. | Remarks
2026-03-04 | FW-101 | ISO-PL-01 | W-04 | WPS-01 | CS / 12.7 | VT (Visual) | Accept
2026-03-05 | FW-102 | ISO-PL-01 | W-07 | WPS-01 | CS / 12.7 | RT (Radiography) | Reject | Porosity
2026-03-06 | FW-102-R1 | ISO-PL-01 | W-02 | WPS-01 | CS / 12.7 | RT (Radiography) | Accept |  | FW-102